## Milestones WIP
Category | Task | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30
Idea Validation and Market Research: | Define the problem the product solves.
Conduct market research to validate the demand.
Identify the target audience and competition.
Create a basic business model and value proposition.
Conceptualization and Planning: | Refine the product concept based on market feedback.
Define the features and functionalities of the product.
Create a high-level project plan and roadmap.
Set initial budget estimates and resource requirements.
Prototyping and Wireframing: | Develop wireframes to visualize the user interface and user experience (UI/UX).
Create a basic prototype to demonstrate core functionalities.
Gather feedback from potential users and stakeholders.
Iterate on the prototype based on feedback.
Technical Feasibility Study: | Assess the technical feasibility of implementing the product.
Define the technology stack and infrastructure requirements.
Identify potential technical challenges and mitigation strategies.
Detailed Design and Architecture: | Create detailed design specifications for each feature.
Define the overall system architecture.
Break down the project into smaller modules or components.
Establish coding standards and development guidelines.
Development (Alpha Version): | Start coding the core features of the product.
Implement the database structure and back-end logic.
Develop the front-end based on the wireframes.
Conduct regular code reviews and testing.
Aim to have an alpha version with basic functionalities.
User Testing (Alpha): | Conduct alpha testing with a limited group of users.
Gather feedback on usability and identify bugs or issues.
Make necessary adjustments and refinements.
Beta Version Development: | Address feedback from alpha testing.
Develop additional features and improvements.
Conduct ongoing testing and bug fixing.
Aim to have a feature-complete beta version.
Beta Testing: | Release the beta version to a larger audience.
Collect feedback from a diverse user group.
Monitor system performance and gather insights.
Iteratively improve based on user feedback.
Pre-Launch Marketing: | Develop a marketing strategy for the product launch.
Create promotional materials and content.
Build anticipation through teasers or pre-launch campaigns.
Final Testing and QA: | Conduct thorough testing on the complete product.
Identify and fix any remaining bugs or issues.
Perform security and performance testing.
Launch: | Release the final version of the product to the public.
Execute marketing and promotional activities.
Monitor server loads and user activity.
Provide customer support and gather feedback.
Post-Launch Optimization: | Analyze user data and feedback post-launch.
Implement updates and improvements based on insights.
Address any unexpected issues or bugs.
Scaling and Growth: | Plan for scalability based on user adoption.
Monitor server performance and optimize infrastructure.
Implement new features to enhance user experience.
Explore partnerships and collaborations for growth.